## Bug Report
DevelopersHub Corporation – Software Quality Assurance
Week 1 Bug Report ¦ Application: To-Do List & Login/Signup System ¦ May 2026
Bug ID | Module | Description | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Environment | Status | Reported By
BUG-001 | Login | No validation on empty login form submission | High | High | 1. Open login page 2. Leave email & password blank 3. Click Login | Validation errors shown for empty fields | Form submits with no error; blank page renders | Chrome 124 / Win11 | Open | QA Team
BUG-002 | Signup | Password mismatch not caught on registration | High | High | 1. Go to signup 2. Enter password: Pass@123 3. Enter confirm: Pass@999 4. Click Register | Error: 'Passwords do not match' | Registration proceeds; app crashes on backend | Chrome 124 / Win11 | Open | QA Team
BUG-003 | Signup | Invalid email format accepted and causes 500 error | Critical | High | 1. Go to signup 2. Enter email: user@@mail 3. Fill other fields 4. Click Register | Inline validation: 'Enter a valid email address' | Form submits; server returns HTTP 500 Internal Server Error | Firefox 125 / macOS | Open | QA Team
BUG-004 | To-Do | Empty task can be created with no title | Medium | Medium | 1. Log in 2. Click Add Task 3. Leave title blank 4. Click Save | Validation error: 'Task title cannot be empty' | Blank task saved and appears in task list | Chrome 124 / Win11 | Open | QA Team
BUG-005 | To-Do | Edit task does not save updated title | High | High | 1. Click edit icon on existing task 2. Modify title text 3. Click Save | Task title updated in list immediately | Edit modal closes but old title remains; update silently fails | Chrome 124 / Win11 | Open | QA Team
BUG-006 | To-Do | Completed filter shows all tasks instead of only completed | Medium | Medium | 1. Mark 2 tasks complete 2. Click 'Completed' filter tab | Only completed tasks displayed | All tasks (active + completed) displayed in Completed tab | Chrome 124 / Win11 | Open | QA Team
BUG-007 | UI | Login form overflows viewport on 375px mobile screen | High | High | 1. Open DevTools 2. Set viewport to 375px 3. Navigate to login page | Responsive layout; no horizontal scrollbar | Login form extends beyond screen width; horizontal scroll appears | Chrome DevTools / Mobile Emulation | Open | QA Team
BUG-008 | UI | Page load time exceeds 3-second threshold (5.2 s recorded) | Medium | Medium | 1. Clear browser cache 2. Open Network tab in DevTools 3. Navigate to home page | Full page load <= 3 seconds | Load time: 5.2 s due to unoptimized image assets (2.1 MB) | Chrome 124 / 100 Mbps connection | Open | QA Team
BUG-009 | UI | Password input field missing placeholder text | Low | Low | 1. Open login or signup page 2. Inspect password input field | Placeholder text indicating expected format (e.g., 'Enter password') | Password field renders with no placeholder; users unaware of requirements | Chrome 124 / Win11 | Open | QA Team

## Summary Dashboard
SQA Week 1 – Bug Report Summary
DevelopersHub Corporation ¦ May 2026
Metric | Count
Total Bugs Reported | 9
Open | 9
In Progress | 0
Resolved | 0
Closed | 0
Severity | Count
Critical | 1
High | 4
Medium | 3
Low | 1
Module | Bugs Found
Login | 1
Signup | 2
To-Do | 3
UI | 3

## SDLC-STLC Reference
SDLC vs STLC – Quick Reference
SDLC Phase | Description | QA Role
1. Planning | Define project scope, timeline, resources | Review requirements, plan test strategy
2. Requirements | Gather and document functional requirements | Analyze requirements for testability
3. System Design | Architect solution, database, UI mockups | Design test cases from design specs
4. Implementation | Developers write and unit-test code | Prepare test environment and test data
5. Testing | Validate software meets requirements | Execute manual & automated test cases
6. Deployment | Release to production environment | Perform smoke & regression testing
7. Maintenance | Monitor, patch, and update the application | Regression test after each update
STLC Phases
STLC Phase | Entry Criteria | Deliverable
1. Requirement Analysis | Requirements document available | Requirements Traceability Matrix (RTM)
2. Test Planning | Requirements analyzed | Test Plan Document
3. Test Case Development | Test plan approved | Test Cases, Test Data
4. Test Environment Setup | Test cases ready | Configured test environment
5. Test Execution | Test environment ready | Test results, Bug Reports
6. Test Closure | All tests executed, bugs fixed or deferred | Test Closure Report, Metrics